## Sheet1
Start Week Commencing 12/08 |  | TASKS | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
|  | 1 | Complete Planning/GDD | Start Blocking Out Level | Hard Surface Mats Blocks
Fill colour when complete |  | 2 | Set Specific Roles and Tasks | Basic Mechanics Dev | Basic Mechanics Dev
| Complete | 3 | Decide on Prototype Mechanics | TDD
| In Progress | 4 | Initial Setting/Style
5
6
7
8
9
10
Roles:
|  |  | Project Management | Level Design | Coding | Coding
|  |  | UI | 3D
|  |  | Anjies Tasks | Bens Tasks | Cams Tasks | Armandas' Tasks
|  |  | Look at Illustrator | References
|  |  | Think of Colour Pallet for UI | House Parts Modelling
|  |  | Reference Images | Projection Map Textures
Low Poly House
Character?
Items (Assorted)